Strengthening capacities and digital competences in biomedical education through internationalization at home - BIOSINT

E4.4 WORKSHOP FOR DEVELOPMENT OF NEW VIRTUAL COURSES

FACULTY OF MEDICINE, UNIVERSITY OF TUZLA

BOSNIA AND HERZEGOVINA

THE MEETING MINUTES

| # VENUE OF THE MEETING | # DATE |
| --- | --- |
| # UNIVERSITY OF TUZLA, Faculty of Humanities and Social Sciences, # Second Floor, Amphitheatre 2 # Dr. Tihomila Markovića 1, # 75 000 Tuzla, # Bosnia and Herzegovina | # 05 - 06 DEC 2024 |
| HOST PARTNER | MINUTES PREPARED BY |
| # FACULTY OF MEDICINE, UNIVERSITY OF TUZLA, BOSNIA AND HERZEGOVINA | Prof. dr. Jasmin Suljagić Selma Ćebić Babajić |

Table of Contents

- Participants Attending Meeting

- Agenda of Meeting

- Meeting Objectives

- Meeting Notes

- Evaluation of the Meeting

Annexes

- Annex I Attendance list

- Annex II  Photos

- Agenda of meeting

# AGENDA

# Wednesday  04 December 2024

| 04.12.2024. | Arrival of participants at their accommodations |
| --- | --- |

# Thursday  05  December 2024 – UNIVERSITY OF TUZLA

| 09:00-09:30 | Registration | All partners |
| --- | --- | --- |
| 09:30-09:45 | Welcome speech | Prof. dr. Jasmin Suljagić (Vice-Rector) |
| 09:45-10:00 | Presentation of the University of Tuzla, Faculty of Medicine | Representative from Faculty of Medicine of the University of Tuzla |
| 10:00-10:15 | -Presentation of challenges and obstacles with submitting of Periodic report. -Key conclusions to be followed by partners. -What do we have to do? | UniKg |
| 10:15-11:30 | -Presentation of proposed virtual courses -Forming international teams for each proposed course -Defining deadline for developing of proposed virtual courses | UniKg and UES, all partners |
|  | -Discussion about adoption of these courses at councils of each project partner. -Discussion about model which will be used for performing virtual courses. -Discussion about date of starting with virtual courses (piloting T4.6). Do we have virtual classrooms formed at each project partner with available procured equipment? -Discussion about Evaluation of pilot activities (T4.7). | UniKg and UES, all partners |
| 11:30-12:00 | Coffee break | All partners |
| 12:00-13:00 | Review of deliverables within WP4 D4.1 Trainings for teachers in IoC, D4.2 Internationalized existing courses, D4.3 New developed international virtual courses, D4.4 Equipment for digital online teaching platform, D4.5 Virtual classrooms. When and how should we implement them? | UES |
| 13:00-14:00 | Lunch break | Representative from University of Tuzla |
| 14:00-15:00 | Review of deliverables within WP4 (D4.1, D4.2, D4.3, D4.4, D4.5). When and how should we implement them? |  |
| 15:00-17:00 | City tour | All partners |
| 19:00-21:00 | Dinner | All partners |

# FRIDAY 6 December 2024

| 09:00 – 09:30 | Discussion about the tasks with all partners (online) | Geert De Lepeleer |
| --- | --- | --- |
| 09:35-11:00 | Discussion about the following topics: -Activities T3.3-T3.6 -D3.2 Institutional trainings -D3.3 Digital protocols for international students and staff -D3.4 Buddy systems -What we have to do and deadlines? | All partners |
| 11:35-12:00 | Coffee break |  |
| 12:00-13:00 | Disscusion and review of WP5 Impact and dissemination. Tasks for partners. T5.1 Design and implementation of dissemination and exploitation plan T5.2 Making tools for dissemination T5.3 Raising awareness through info-days, symposia and conferences T5.4 Preparation of the interim and final report on dissemination and exploitation activities T5.5 Reporting on impact and sustainability D5.1 Dissemination and exploitation plan | UNISHK |
| 13:00-13:30 | Project consortium meeting. Executive board meeting. | All partners |
| 13:30 – 14:00 | Lunch | All partners |

- Meeting objectives

The main objectives of this workshop (WP4 - Development of new virtual courses) were:

- Defining the general principles that would apply to the documents regarding deliverable D3.2 Institutional training,  D3.3 Digital protocols for international students and staff and D3.4 Buddy systems.

- Selecting existing subjects for internationalization and define the form and content of the courses

- identify exactly to what stage each partner has fulfilled the plans and how and with what dynamics the delivery can be fully completed in all WB institutions (fully functional virtual classroom)

- to define the general framework / principles of the document(s) that each WB partner should submit to the UES and then to UniKg, which will compile all the individual documents and enter them as a ZIP archive in the EU portal of the project.

- Meeting Notes

- Welcome Speech and Brief Information about Project

Prof. Dr. Jasmin Suljagić, Vice-Rector of the University of Tuzla, gave a welcome speech to all partners and prof. Melisa Lelić presented an overview the Faculty of Medicine.

Participants were informed that the representative of KU Leuven, will not be present at the meeting for justified reasons, but that they will join online on the second day at the beginning of the meeting.

- Presentations of Partner Institutions and Discussion Points

Assistent teacher dr. Božidar Pindović from the Faculty of Medical Sciences, University of Kragujevac, discussed challenges in periodic report submission.

1. Project Officer Feedback – The new project officer expressed concerns about deliverables and project timelines:

- Explanations were provided regarding delays

- Six deliverables were missing from the platform

- Geert De Lepeleer assisted in identifying the missing deliverables

- Arrangements for technical details will be made during the workshop

- Deadline to upload documents: 17 December

- Strict directive: No further delays allowed

2. Deliverables:

- Deliverables D3.2 to D3.4 are pending

- WP4: Training for teachers in IoC and curriculum internationalization from D4.1 to D4.3 need to be completed, in preparation for the start of implementation of virtual classrooms (D4.5)

- Geert De Lepeleer assisted in identifying the missing deliverables

- Arrangements for technical details will be made during the workshop

- Deadline to upload documents: 17 December

- Strict directive: No further delays allowed

3. Virtual Classroom Equipment:

- Equipment procurement checklist to be completed

- Documents related to equipment must be scanned and uploaded

- University of Tuzla expects to have classroom equipment installed within one month

4. Institutional Trainings, Digital protocols and Buddy system:

- UNTZ requires an additional institutional training for 30 people and needs to establish digital protocols and buddy system

- University of East Sarajevo (UES) also requires documentation of digital protocols and buddy system, which have been integrated and initiated, as well as documentation of institutional training, which it completed

5. Course ECTS Credits – Variations in ECTS credits across institutions:

- East Sarajevo: 1 ECTS

- Tirana: Pending information

- Tuzla: 2-3 ECTS

- Montenegro: 4 ECTS

- Shkodra: 2 ECTS

- Mostar: 1 ECTS

A consensus was reached that uniformity in credits is not mandatory.

6. Piloting and adoption of courses:

- Piloting to occur from March to June

- Use of consortium teachers to facilitate courses

- Challenges noted for Tirana due to lack of Faculty support

- Key Deliverables and Deadlines

1. BIOSINT Template:

- All syllabi to include BIOSINT logo, Erasmus co-funded logo, Faculty logo, BIOSINT disclaimer

2. Documentation:

- Only summaries to be in English

- Complete scanning and uploading of documents related to equipment

3. Virtual courses:

- Development of international teams for course creation

- Deadlines: Names for virtual course teams by Tuesday and Brochure and deliverables finalization by 17 December 2024

- Other discussions

1. Nutrition Courses Alignment:

- Connection with the Department of ZVS for course piloting

2. Challenges in Albania:

- Implementation of courses delayed until 2027/2028 due to study program innovation cycles

- Written official explanations required for delays

- Conclusion

1. Partners to adopt all three new virtual courses

2. Academic councils to approve piloting by the next semester

3. Online courses to be finalized as elective offerings by June

4. Albania to address challenges with implementation

5. Upload missing documents/deliverables by 17 December, partners to ensure all deliverables are completed promptly

6. Finalize team names for virtual courses by Tuesday

Meeting adjourned by Vice-Rector Jasmin Suljagić.

- On the second day of the training, Geert De Lepeleer presented a guide for internationalization of curricula, which was followed by a discussion disscusion. A decision was made to upload the guide/brochure as part of the Deliverable on Trainings for teachers in IoC. Mr De Lepeleer was informed about issues related to the Albanian study program, which will be adopted in June 2025, for the 2027/2028 academic year, and that pilot teaching is planned to start in February 2025. Certificates will be issued to Albanian students who attend virtual classrooms during the pilot phase until their institutions officially adopt the internationalized curriculum.

- Teacher certification and Course implementation

1. English certificates will be provided by June 2025, by an official school of foreign languages for teachers that require them to hold lectures as part of the virtual classrooms.

2. Internationalized courses to be implemented according to each university's regulations.

- WORK PACKAGE 5 – Dissemination

1. Budget allocation for printing materials and dissemination items (e.g., notes, pencils, bags, bottles, USB sticks) was discussed and a plan is to be formed for all printing and dissemination activities for the next year.

2. UMT, in collaboration with UES, to develop the project website. UNISHK has six newsletters planned, two of which have been made.

3. Topics are to be defined for research articles. Two teams from two universities to work on research papers:

- Joint paper: Challenges of internationalization at home in Western Balkan countries (biomedical studies).

- Second paper: One original and one review paper focusing on topics like the buddy system.

Discussion on student satisfaction questionnaires and their inclusion in the research. Deadline: to be completed by the end of the project

At the end, the Consortium's Executive Board meeting was held where the current status of the BIOSINT project's budget/financial plan was discussed. UniKG informed the partners about the reduced ammount of additional pre-financing that was received from EACEA following the submittion of the periodic report due to the lack of spending by BIOSINT partners. Each partner was informed in regards to the individual reduced summs that they will be receiving. A real financial rundown of all the partner's spending up until now was needed and the partners were instructed to begin staff payments. It was suggested that, following the payment's of the staff costs, to send the EACEA project officer a financial report and request a second payment of the remaining additional pre-financing that was witheld. The officer would also be asked for a re-distribution of the remaining funds so an additional on-site meeting could be held, organised by UniKG. Further financial clarification was required on the financial plan which will be elaborated to the partners by UniKG in the coming weeks. The next meeting will be held in Tirana, with a tentative date set for 5-6 June 2025 (arrival on 3 June, departure on 6 June). Regular online meetings are to be held every other Monday from 13:00 to 14:00, with the next meeting scheduled for 16 December 2024.

ANNEX II - PHOTOS OF THE MEETING